Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 01 August 2026 |
| --- | --- |
| Team ID |  |
| Project Name | TradeX – Smart Stock Trading and Portfolio Management (MERN) |
| Maximum Marks | 5 Marks |

# Product Backlog & Sprint Planning

| Sprint | Functional Requirement (Epic) | User Story No. | User Story / Task | Story Points | Priority | Team Member |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Registration | USN-1 | As a user, I can register as a trader using my username, email and password. | 3 | High | TradeX Team |
| Sprint-1 | Authentication | USN-2 | As a user, I can log in securely using my registered email and password. | 2 | High | TradeX Team |
| Sprint-1 | Authentication | USN-3 | As a user, my password is encrypted with bcrypt and API routes are secured with JWT authentication. | 5 | High | TradeX Team |
| Sprint-1 | Authorization | USN-4 | As a user, I can access role-specific features based on my account type (Trader or Admin). | 3 | High | TradeX Team |
| Sprint-1 | User Profile | USN-5 | As a trader, I can view and update my user profile, account balance, and deposit/withdraw funds. | 3 | Medium | TradeX Team |
| Sprint-2 | Market Listings | USN-6 | As a trader, I can browse US stock listings and search or filter stocks by symbol or company name. | 3 | High | TradeX Team |
| Sprint-2 | Real-Time Market Data | USN-7 | As a trader, I can view real-time stock prices, company details, and historical market trend charts. | 5 | High | TradeX Team |
| Sprint-2 | Virtual Portfolios | USN-8 | As a trader, I can create and manage multiple virtual portfolios to test diverse investment strategies. | 3 | High | TradeX Team |
| Sprint-2 | Paper Trading | USN-9 | As a trader, I can place buy and sell orders for stocks by selecting quantities and confirming execution. | 5 | High | TradeX Team |
| Sprint-2 | Portfolio Holdings | USN-10 | As a trader, I can view my current stock holdings, overall portfolio value, and real-time profit/loss. | 3 | High | TradeX Team |
| Sprint-2 | Order Management | USN-11 | As a trader, I can review all pending and executed stock orders with real-time status updates. | 3 | Medium | TradeX Team |
| Sprint-3 | Transaction History | USN-12 | As a trader, I can access a complete transaction log of all buy/sell activities with exact timestamps. | 3 | High | TradeX Team |
| Sprint-3 | Strategy Analytics | USN-13 | As a trader, I can analyze historical stock performance and refine my trading strategies over time. | 3 | Medium | TradeX Team |
| Sprint-3 | Global App State | USN-14 | As a user, I can experience persistent navigation and authentication state using React Context API. | 3 | Medium | TradeX Team |
| Sprint-3 | Admin Dashboard | USN-15 | As an administrator, I can view overall platform statistics, user count, and total trading volume. | 5 | High | TradeX Team |
| Sprint-3 | Admin User Control | USN-16 | As an administrator, I can view all registered users and manage account statuses or security permissions. | 3 | Medium | TradeX Team |
| Sprint-3 | Admin Market Control | USN-17 | As an administrator, I can manage stock listings, update market data feeds, and monitor global orders. | 5 | Medium | TradeX Team |
| Sprint-3 | MongoDB Schemas | USN-18 | As a developer, I can structure Mongoose schemas for Users, Stocks, Orders, and Transactions. | 5 | High | TradeX Team |
| Sprint-3 | MVC API Architecture | USN-19 | As a developer, I can structure backend REST API routes and controllers following MVC principles. | 3 | High | TradeX Team |
| Sprint-3 | Environment Setup | USN-20 | As a developer, I can configure Vite React frontend and Node/Express/MongoDB backend environment variables. | 2 | High | TradeX Team |
| Sprint-3 | System Deployment | USN-21 | As a user, I can access the deployed TradeX full-stack application securely online. | 3 | High | TradeX Team |

# Project Tracker, Velocity & Sprint Schedule

Since the project duration is 61 days (1 August 2026 to 30 September 2026), divide it into 3 sprints.

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 16 | 20 Days | 01 Aug 2026 | 20 Aug 2026 | 16 | 20 Aug 2026 |
| Sprint-2 | 22 | 21 Days | 21 Aug 2026 | 10 Sep 2026 | 22 | 10 Sep 2026 |
| Sprint-3 | 32 | 20 Days | 11 Sep 2026 | 30 Sep 2026 | 32 | 30 Sep 2026 |

## Velocity

Total Story Points = 70
Total Sprints = 3

Average Velocity per Sprint:
70 ÷ 3 = 23.3 ≈ 23 Story Points/Sprint

Average Daily Velocity:
70 ÷ 61 = 1.15 ≈ 1.2 Story Points/Day

## Burndown Chart Data

| Day | Remaining Story Points |
| --- | --- |
| 1 | 70 |
| 2 | 69 |
| 3 | 68 |
| 4 | 66 |
| 5 | 65 |
| 6 | 64 |
| 7 | 63 |
| 8 | 62 |
| 9 | 61 |
| 10 | 60 |
| 11 | 58 |
| 12 | 57 |
| 13 | 56 |
| 14 | 55 |
| 15 | 54 |
| 16 | 52 |
| 17 | 51 |
| 18 | 50 |
| 19 | 49 |
| 20 | 48 |

## Project Summary

| Metric | Value |
| --- | --- |
| Total User Stories | 21 |
| Total Story Points | 70 |
| Project Duration | 61 Days (01 Aug 2026 – 30 Sep 2026) |
| Total Sprints | 3 |
| Sprint Duration | 20–21 Days/Sprint |
| Average Velocity | 23 Story Points/Sprint |
| Average Daily Velocity | ≈ 1.2 Story Points/Day |